DFSS_PILOT_MEASUREMENT_ACTIVATION_TEMPLATE_V1

Cert-Expert | Bilingual Fill-in Template / Zweisprachige Ausfüllvorlage

| Field / Feld | Content / Inhalt |
| --- | --- |
| Document / Dokument | DFSS_PILOT_MEASUREMENT_ACTIVATION_P05_SecuGuard_UPDATED_2026-06-05 |
| Purpose / Zweck | Capture real P05 baseline and pilot-measurement evidence for SecuGuard NC closure after surveillance audit. No invented closure evidence; interview-based closure hypotheses are marked as such. |
| Current gate status / Aktueller Gate-Status | NOT READY FOR PILOT VALIDATION REPORT - DATA COLLECTION REQUIRED; READY FOR ACTIVE P05 MEASUREMENT / EVIDENCE REQUEST |
| Project context / Projektkontext | P05 SecuGuard: ISO 45001/ISO 14001 surveillance audit NC closure. 5 major ISO 45001 NCs, 1 minor ISO 45001 NC, 1 minor ISO 14001 NC. Evidence status: 0 closure proofs received as of interview. |
| Working boundary / Arbeitsgrenze | No invented pilot data, no invented target values, no product design, no UI, no data model, no software architecture. / Keine erfundenen Pilotdaten, keine erfundenen Zielwerte, kein Product Design, keine UI, kein Datenmodell, keine Softwarearchitektur. |
| Version / Version | V1.0 ¦ Fill-in template / Ausfüllvorlage |
| Owner / Verantwortlich | Cert-Expert / Marwan Mahra (working owner); customer contact: M. Marquardt; external dependency: Inductus/FASI/Betriebsarzt |
| Date / Datum | 2026-06-05 |

How to use / Anwendung: Fill the yellow cells where applicable. Use Project IDs P01-P05. Every claim in a later report must have an Evidence ID. / Gelbe Felder ausfüllen. Projekt-IDs P01-P05 verwenden. Jede spätere Report-Aussage braucht eine Evidence-ID.

# 0. Quick Status / Schnellstatus

| Question / Frage | Answer / Antwort |
| --- | --- |
| Are real quantitative pilot values already available? / Liegen bereits echte quantitative Pilotwerte vor? | [ ] Yes [ ] No [x] Partly - NC count, exact NC chapters, deadline, evidence needs and interview-based closure hypotheses captured; no accepted closure evidence yet; V-01/V-03 hours still TBD |
| Are projects currently measurable from now on? / Können Projekte ab jetzt messbar begleitet werden? | [x] Yes, from 2026-05-28 finding date; active closure request still pending [ ] No [ ] Partly |
| Can a Pilot Validation Report be created now? / Kann jetzt ein Pilot Validation Report erstellt werden? | [ ] Yes [x] No, Data Collection Required; 0/7 NC closure evidence received |
| Decision / Entscheidung | [x] Activate measurement system and P05 evidence request [ ] Rework [ ] Report later |

# 1. Project Portfolio Overview / Projektportfolio-Übersicht

Fill one row per ongoing project. / Eine Zeile pro laufendem Projekt ausfüllen.

| Project ID / Projekt-ID | Type / Typ | Norms / Normen | SDLs / Services | Service model / Leistungsmodell | Start | Audit date / Audittermin | Main blocker / Hauptblocker | Readiness / Ampel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| P01 | Initial certification / Erstzertifizierung | ISO 9001 + DIN 77200-1/-2 | 2 SDLs + refugee/asylum accommodation / 2 SDLs + Flüchtlings-/Asylunterkünfte | Documentation basis / Dokumentenbasis | [fill] | [set / gesetzt] | Insurance evidence/sum / Versicherungsnachweis/-summe | [ ] Green [ ] Yellow [ ] Red |
| P02 | Initial certification / Erstzertifizierung | ISO 9001 + DIN 77200-1/-2 | 2 SDLs + refugee/asylum accommodation / 2 SDLs + Flüchtlings-/Asylunterkünfte | Documentation basis / Dokumentenbasis | [fill] | [not set / offen] | Clearance certificate / Unbedenklichkeitsbescheinigung | [ ] Green [ ] Yellow [ ] Red |
| P03 | Surveillance audit / Überwachungsaudit | [fill] | [fill] | Continuity / Betreuung | [fill] | [fill] | Time pressure / Zeitdruck | [ ] Green [ ] Yellow [ ] Red |
| P04 | Surveillance audit / Überwachungsaudit | [fill] | [fill] | Continuity / Betreuung | [fill] | [fill] | Time pressure / Zeitdruck | [ ] Green [ ] Yellow [ ] Red |
| P05 | Surveillance audit / NC closure (Ü1) | ISO 45001, ISO 14001 | SecuGuard Service GmbH, Berlin; company-wide/admin site after relocation; sampled project with contract evidence issue | Continuity / Ü1 follow-up with customer; NC closure evidence request pending | 2026-05-28 | 2026-05-28 finding; closure deadline 2026-06-30 | 0 closure evidence received; customer email pending; M3 external partner dependency; m1 HR file missing; m2 Strom/Wasser baseline missing | [ ] Green [ ] Yellow [x] Red |

# 2. Project Setup Record / Projekt-Steckbrief

Copy this block if more detailed project records are needed. / Diesen Block bei Bedarf pro Projekt kopieren.

| Field / Feld | Input / Eingabe | Notes / Hinweise |
| --- | --- | --- |
| Project ID / Projekt-ID | P05 | Use P01-P05. |
| Anonymized project name / Anonymisierter Projektname | P05-NC-closure-2026 (internal: SecuGuard Service GmbH) | No client name required. / Kein Kundenname erforderlich. |
| Project type / Projekttyp | [ ] Initial cert [x] Surveillance [x] Other: NC closure after Ü1 | Select one. |
| Norms / Normen | [ ] ISO 9001 [ ] DIN 77200-1/2 [x] ISO 14001 [x] ISO 45001 | Mark all applicable. |
| SDLs / Security service lines | Company-wide Berlin; admin site after relocation; sampled operational project with contract/wachbuch evidence | Example: Empfangsdienst, Revierdienst, Veranstaltung, Flüchtlings-/Asylunterkunft. |
| Special DIN 77200-2 scope / Besonderer DIN-77200-2-Scope | n/a | If applicable. / Falls zutreffend. |
| Service model / Leistungsmodell | [ ] Documentation basis [ ] Done-for-you [ ] Done-with-you [x] Continuity | Do not mix models without comment. / Modelle nicht ohne Kommentar vermischen. |
| Project start / Projektstart | 2026-05-28 | Approximate date is acceptable. / Ungefähr reicht. |
| Audit date / Audittermin | 2026-05-28 (finding); closure 2026-06-30 | If not set, give reason. / Wenn offen, Grund angeben. |
| Main project situation / Hauptsituation | 5 major ISO 45001 + 1 minor ISO 45001 + 1 minor ISO 14001 from audit 28.05.2026; 0/7 closed; no closure evidence received yet; customer request email required | Example: strong time pressure, missing evidence, referral project. |
| Current system used / Aktuell genutztes System | HQ + OneDrive Ü1 + interview notes; customer evidence request not sent yet; templates needed: Mutterschutz-Unterweisung and Wachbuch-Guide | Drive, Forms, Excel, SharePoint, project folder, etc. |
| Owner / Verantwortlich | Cert-Expert / Marwan Mahra; customer M. Marquardt; external partner: Inductus for FASI/Betriebsarzt | Validation Lead / project owner. |

# 3. Timeline Capture / Zeitpunkterfassung

These dates create the baseline. Do not estimate if unknown; write TBD. / Diese Daten bilden die Baseline. Wenn unbekannt: TBD eintragen.

| Timepoint / Zeitpunkt | P01 | P02 | P03 | P04 | P05 | Comment / Kommentar |
| --- | --- | --- | --- | --- | --- | --- |
| Offer accepted / Angebot angenommen |  |  |  |  | TBD | TBD |
| Kickoff / Projektstart |  |  |  |  | 2026-05-28 | Measurement phase / NC start |
| Forms or company list sent / Forms oder Unternehmensliste gesendet |  |  |  |  | TBD - evidence request email pending | Need cooperative customer email with grouped evidence request |
| First client documents received / Erste Kundenunterlagen erhalten |  |  |  |  | 2026-05-28 | Ü1 deviation doc from audit |
| Complete start dataset received / Vollständiger Startdatensatz erhalten |  |  |  |  | No | 0 closure evidence received; customer/partner inputs pending |
| Critical evidence complete / Kritische Nachweise vollständig |  |  |  |  | No | 0/7 NC closed; no closure proof received |
| Documents drafted / Dokumente erstellt |  |  |  |  | Partial | IM/IMS protocol exists; Umweltkennzahlenblatt and IM protocol by Cert-Expert; Mutterschutz template + Wachbuch-Guide pending |
| Technical review completed / Fachreview abgeschlossen |  |  |  |  | No / Partial | Abweichungsdokumentation reviewed; closure evidence not yet technically reviewed |
| Audit package ready / Auditpaket fertig |  |  |  |  | n/a | n/a — closure phase |
| Audit date / Audittermin |  |  |  |  | 2026-05-28 | 2026-05-28 |
| Audit result / Auditergebnis |  |  |  |  | 7 NCs open | 7 NCs open (5+2) |

# 4. Blocker and Rework Log / Blocker- und Nacharbeitslog

| ID | Project / Projekt | Blocker or issue / Blocker oder Thema | S0 relation / S0-Bezug | Owner | Due date / Frist | Status | Evidence ID / Evidenz-ID |
| --- | --- | --- | --- | --- | --- | --- | --- |
| B-01 | P05 | M1 ISO 45001 8.1.2 - Mutterschutz: signed workplace-specific instruction missing | S0-03, S0-05, DR-03, DR-08 | M. Marquardt + Cert-Expert template | 2026-06-30 | [x] Open - template/signature pending | EV-SG-004 |
| B-02 | P05 | M2 ISO 45001 5.4 - consultation/worker participation evidence missing; IM/IMS meeting protocol required | S0-03, S0-05, DR-08, DR-18 | M. Marquardt + Cert-Expert | 2026-06-30 | [x] Open - protocol evidence pending | EV-SG-005 |
| B-03 | P05 | M3 ISO 45001 6.1.4 - FASI/Betriebsarzt site-specific service + annual report missing; Inductus dependency | S0-03, S0-06, DR-09 | Cert-Expert to contact Inductus; customer support if needed | 2026-06-30 | [x] Open - external partner dependency | EV-SG-006 |
| B-04 | P05 | M4 ISO 45001 9.1 - Einsatzleiter monitoring not audit-proof; Wachbuch entry/guide needed | S0-03, S0-05, DR-08, DR-11 | Customer/Einsatzleiter + Cert-Expert guide | 2026-06-30 | [x] Open - wachbuch excerpt pending | EV-SG-007 |
| B-05 | P05 | M5 ISO 45001 8.1.1 - sampled project contract exists but was not found during audit | S0-03, DR-03, DR-12, DR-13 | Customer + Cert-Expert evidence filing | 2026-06-30 | [x] Open - contract request pending | EV-SG-008 |
| B-06 | P05 | m1 ISO 45001 7.2 - full HR/personnel file for Prokuristin missing | S0-03, DR-22 | Customer / M. Marquardt | 2026-06-30 | [x] Open - full personnel file pending | EV-SG-009 |
| B-07 | P05 | m2 ISO 14001 10.3 - environmental baselines after relocation missing; Strom/Wasser affected | S0-03, DR-17, DR-18, DR-19 | Customer + Cert-Expert | 2026-06-30 | [x] Open - meter/readings or invoices pending | EV-SG-010 |
| B-08 | P05 | Grouped customer evidence request not sent; closure evidence 0/7 received | S0-03, S0-05, S0-08, DR-20, DR-21 | Cert-Expert | 2026-06-25 | [x] Open - next critical action | EV-SG-011 |
| B-09 |  |  |  |  |  | [ ] Open [ ] In progress [ ] Closed | EV- |
| B-10 |  |  |  |  |  | [ ] Open [ ] In progress [ ] Closed | EV- |

# 5. Evidence Register / Evidenzregister

Every later report statement must reference an Evidence ID. / Jede spätere Report-Aussage braucht eine Evidenz-ID.

| Evidence ID / Evidenz-ID | Project / Projekt | Reference / Bezug | Source / Quelle | Date / Datum | Owner | Method / Methode | Status | Decision / Entscheidung |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| EV-SG-001 | P05 | Major NCs M1-M5, DEKRA Abweichungsdokumentation | DEKRA deviation document / OneDrive Ü1 | 2026-05-28 | Dr. Kira Kultus / Cert-Expert review | Document review | captured / in review | No - NCs open |
| EV-SG-002 | P05 | Minor NCs m1-m2, DEKRA Abweichungsdokumentation | DEKRA deviation document / OneDrive Ü1 | 2026-05-28 | Dr. Kira Kultus / Cert-Expert review | Document review | captured / in review | No - NCs open |
| EV-SG-003 | P05 | Ü1 forms per NC / closure forms | OneDrive Ü1 / customer completion | TBD | M. Marquardt + Cert-Expert | Form completion | open | No |
| EV-SG-004 | P05 | M1 signed workplace-specific Mutterschutz instruction | Customer signed instruction after Cert-Expert template | TBD | M. Marquardt | Customer signature / document review | open | TBD |
| EV-SG-005 | P05 | M2 IM/IMS meeting protocol on consultation and worker participation | Cert-Expert protocol + customer confirmation | TBD | M. Marquardt + Cert-Expert | Protocol review | open | TBD |
| EV-SG-006 | P05 | M3 FASI/Betriebsarzt annual report and site-specific service evidence | Inductus / FASI / Betriebsarzt | TBD | Cert-Expert to contact Inductus | External partner evidence | open - dependency | TBD |
| EV-SG-007 | P05 | M4 Wachbuch excerpt: Einsatzleiter sample check incl. Arbeitsschutz/Qualität/Umwelt/customer requirements | Customer Wachbuch + Cert-Expert guide | TBD | Customer/Einsatzleiter | Document review | open | TBD |
| EV-SG-008 | P05 | M5 contract for sampled project | Customer archive / prior USB evidence / project file | TBD | Customer + Cert-Expert | Document retrieval | open | TBD |
| EV-SG-009 | P05 | m1 personnel file for Prokuristin | Customer HR records | TBD | Customer | Document review | open | TBD |
| EV-SG-010 | P05 | m2 Strom/Wasser baseline after relocation | Customer meter readings/invoices | TBD | Customer + Cert-Expert | Data review | open | TBD |
| EV-SG-011 | P05 | Grouped cooperative customer evidence request email | Cert-Expert email / sent record | TBD | Cert-Expert | Communication evidence | not sent | TBD |
| EV-012 |  | [DR/S0/RC/V] |  |  |  | [VR-GATE/DOC/PIL/CUST/EXP/AUD/NEG] | [Open/In Review/Accepted/Rework] | [Pass/PWC/Fail/TBD] |
| EV-013 |  | [DR/S0/RC/V] |  |  |  | [VR-GATE/DOC/PIL/CUST/EXP/AUD/NEG] | [Open/In Review/Accepted/Rework] | [Pass/PWC/Fail/TBD] |
| EV-014 |  | [DR/S0/RC/V] |  |  |  | [VR-GATE/DOC/PIL/CUST/EXP/AUD/NEG] | [Open/In Review/Accepted/Rework] | [Pass/PWC/Fail/TBD] |
| EV-015 |  | [DR/S0/RC/V] |  |  |  | [VR-GATE/DOC/PIL/CUST/EXP/AUD/NEG] | [Open/In Review/Accepted/Rework] | [Pass/PWC/Fail/TBD] |

# 6. Baseline Data Sheet / Baseline-Datenblatt

| Baseline area / Baseline-Bereich | Metric or observation / Kennzahl oder Beobachtung | P01 | P02 | P03 | P04 | P05 | Evidence ID |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Lead time / Durchlaufzeit | Days from full dataset to readiness status / Tage vom vollständigen Startdatensatz bis Readiness-Status |  |  |  |  | Finding date 2026-05-28; active evidence request not sent yet; complete start dataset not received | EV-SG-001/011 |
| Client effort / Kundenaufwand | Client hours, interactions, open tasks / Kundenstunden, Interaktionen, offene Aufgaben |  |  |  |  | Estimated 5-6 customer actions; no measured hours/interactions yet | Interview note / EV-SG-011 |
| Evidence completeness / Nachweisvollständigkeit | Missing critical evidence / Fehlende kritische Nachweise |  |  |  |  | 0 closure evidence received; 7 NCs open; templates/request pending | EV-SG-001/002/003 |
| Audit package / Auditpaket | Ready, incomplete, rework needed / fertig, unvollständig, Nacharbeit nötig |  |  |  |  | Not ready; NC closure package not built; Abweichungsdokumentation captured | EV-SG-001/002/003 |
| Audit questions / Audit-Rückfragen | Questions, document searches, follow-up evidence / Rückfragen, Suchaufwand, Nachreichungen |  |  |  |  | 7 formal NCs; likely evidence questions: signature, protocol, annual report, wachbuch excerpt, contract, HR file, Strom/Wasser baseline | EV-SG-001/002 |
| Support load / Supportlast | Support cases or client confusion / Supportfälle oder Kundenüberforderung |  |  |  |  | TBD; first customer email should be cooperative/entlastend; track replies and confusion | EV-SG-011 |
| Continuity / Betreuung | Fristen, ZKM, renewal plan, follow-up tasks / Fristen, ZKM, Renewal-Plan, Folgeaufgaben |  |  |  |  | Deadline 2026-06-30; direct post-audit closure sprint expected, but active closure gap exists | EV-SG-003/011 |

# 7. S0 Gate Checklist / S0-Muss-Gate-Checkliste

S0 gates are hard Pass/Fail gates. A fail creates blocker/rework, not a normal to-do. / S0-Gates sind harte Pass/Fail-Gates. Ein Fail erzeugt Blocker/Rework, kein normales To-do.

| Gate | Requirement / Anforderung | DR relation / DR-Bezug | Owner | Status | Evidence ID |
| --- | --- | --- | --- | --- | --- |
| S0-01 | No binding audit planning without documented certification readiness status and classified audit blockers. / Keine verbindliche Auditplanung ohne dokumentierten Zertifizierungsfähigkeitsstatus und klassifizierte Auditblocker. | DR-01, DR-10 | Cert-Expert | [x] Fail - 7 NCs open; no closure status package | EV-SG-001/002 |
| S0-02 | Every scope element is linked to SDL, object/order, evidence and owner. / Jeder Scope-Bestandteil ist SDL, Objekt/Auftrag, Nachweisen und Verantwortlichen zugeordnet. | DR-02 | Cert-Expert | [x] Fail - sampled contract/project evidence not audit-proof | EV-SG-008 |
| S0-03 | Critical evidence is complete, effective or covered by accepted follow-up logic before audit release. / Kritische Nachweise sind vor Auditfreigabe vollständig, wirksam oder mit akzeptierter Nachreichlogik versehen. | DR-03 | Cert-Expert + customer | [x] Fail - 0 closure evidence received | EV-SG-004 to EV-SG-010 |
| S0-04 | Critical documents and scope decisions receive technical review before customer or audit release. / Kritische Dokumente und Scope-Entscheidungen erhalten ein Fachreview vor Kunden- oder Auditfreigabe. | DR-04, DR-24 | Cert-Expert | [ ] TBD - closure docs/templates not reviewed yet | EV-SG-011 |
| S0-05 | Every customer task has owner, due date, priority, purpose and audit-readiness impact. / Jede Kundenaufgabe besitzt Verantwortlichen, Frist, Priorität, Zweck und Auditwirkung. | DR-08, DR-20, DR-21 | Cert-Expert | [x] Fail - customer request not sent; owners/actions not yet confirmed | EV-SG-011 |
| S0-06 | External mandatory partners/evidence are identified with procurement path or responsibility. / Externe Pflichtpartner/-nachweise sind mit Beschaffungspfad oder Verantwortlichkeit dokumentiert. | DR-09 | Cert-Expert | [x] Fail - external dependencies identified, procurement/evidence path not yet proven | EV-SG-006 |
| S0-07 | Every active SDL/object file contains minimum evidence or justified deviation. / Jede aktive SDL-/Objektakte enthält Mindestnachweise oder eine begründete Abweichung. | DR-11 | Cert-Expert + customer | [x] Fail - object/project evidence incomplete; wachbuch/contract pending | EV-SG-007/008 |
| S0-08 | Version safety, SDL/employee release, expert/automation review and renewal logic are controlled. / Versionssicherheit, SDL-/Mitarbeiterfreigabe, Fachreview/Automationsreview und Betreuung/Renewal sind kontrolliert. | DR-13, DR-17, DR-22, DR-24 | Cert-Expert | [x] Fail - release/version/evidence logic not controlled yet | EV-SG-003/011 |

# 8. Readiness Status / Audit-Readiness-Ampel

| Project / Projekt | Green / Grün | Yellow / Gelb | Red / Rot | Reason / Begründung | Next critical action / Nächster kritischer Schritt |
| --- | --- | --- | --- | --- | --- |
| P01 | [ ] | [ ] | [ ] |  |  |
| P02 | [ ] | [ ] | [ ] |  |  |
| P03 | [ ] | [ ] | [ ] |  |  |
| P04 | [ ] | [ ] | [ ] |  |  |
| P05 | [ ] | [ ] | [x] | 7 NCs open; 0/7 closure evidence; customer evidence request not sent; S0-03/S0-05/S0-06 fail | Prepare/send cooperative evidence request; create Mutterschutz template + Wachbuch-Guide; contact Inductus |

# 9. Pilot Data Collection V-01 to V-10 / Pilotdatenerfassung V-01 bis V-10

| V-ID | Data requirement / Datenbedarf | Project(s) / Projekt(e) | Value or observation / Wert oder Beobachtung | Owner | Evidence ID | Status |
| --- | --- | --- | --- | --- | --- | --- |
| V-01 | Days from complete start dataset to certification readiness status / Tage vom vollständigen Startdatensatz bis Zertifizierungsfähigkeitsstatus | P05 | TBD - Finding date 2026-05-28 captured; complete start dataset not received; customer evidence request pending | Cert-Expert | EV-SG-011 | [x] Open |
| V-02 | Days before audit when audit package is ready / Tage vor Audit, an denen Auditpaket prüfbereit ist | P05 | n/a closure phase; pre-audit readiness failed in retrospect; no clean Ü-audit checklist used | Cert-Expert | EV-SG-001 | [ ] Partly |
| V-03 | Client effort by service model: hours, interactions, tasks / Kundenaufwand je Leistungsmodell: Stunden, Interaktionen, Aufgaben | P05 | Estimated 5-6 customer actions; internal effort estimate <= 2h for M1/M2/M4/M5 only; not measured | Cert-Expert | EV-SG-011 | [x] Open |
| V-04 | Audit-readiness gaps by severity / Audit-Readiness-Lücken nach Kritikalität | P05 | 5 Major ISO 45001 + 1 Minor ISO 45001 + 1 Minor ISO 14001 open | Cert-Expert | EV-SG-001/002 | [x] Captured |
| V-05 | Software-only or documentation-basis segment fit / Segmentfit Software-only bzw. Dokumentenbasis | P05 | Continuity/NC closure service model; not software-only; segment-fit to be assessed after response | Cert-Expert | EV-SG-011 | [x] Open |
| V-06 | CEKS/knowledge coverage for norm, SDL, qualification and audit logic / CEKS-/Wissensabdeckung für Norm-, SDL-, Qualifikations- und Auditlogik | P05 | Knowledge gaps: ISO 45001/14001 surveillance checklist, Mutterschutz template, Wachbuch guide, partner evidence path | Cert-Expert | EV-SG-011 | [x] Open |
| V-07 | Auditor/expert review of audit package / Auditoren- oder Expertenreview des Auditpakets | P05 | DEKRA deviation document captured; auditor verification pending | Cert-Expert | EV-SG-001/002/003 | [ ] Partly |
| V-08 | SDL/object file completeness / Vollständigkeit der SDL-/Objektakte | P05 | Incomplete: contract, wachbuch evidence, Prokuristin HR file, Strom/Wasser baseline pending | Cert-Expert + customer | EV-SG-007/008/009/010 | [x] Captured |
| V-09 | Continuity: ZKM, deadlines, renewal, effectiveness / Betreuung: ZKM, Fristen, Renewal, Wirksamkeit | P05 | Deadline 2026-06-30; external dependency Inductus; action gap since 2026-05-28 captured | Cert-Expert | EV-SG-003/006/011 | [x] Captured |
| V-10 | Reverse factors: overload, norm language, wrong model, complexity / Reverse-Faktoren: Überforderung, Normsprache, falsches Modell, Komplexität | P05 | Reverse risks: norm language, customer overwhelm, external partner bottleneck, weak evidence filing; not tested | Cert-Expert | EV-SG-011 | [x] Open |

# 10. DR Execution Log DR-01 to DR-24 / DR-Ausführungslog DR-01 bis DR-24

Use Pass / Pass with Controls / Fail / TBD. Do not close a DR without Evidence ID. / Pass / Pass with Controls / Fail / TBD verwenden. Keine DR ohne Evidenz-ID schließen.

| DR-ID | Validation object / Validierungsobjekt | Project / Projekt | Method / Methode | Evidence ID | Result / Ergebnis | Rework / Nacharbeit |
| --- | --- | --- | --- | --- | --- | --- |
| DR-01 | Certification readiness status / Zertifizierungsfähigkeitsstatus | P05 | VR-GATE / VR-DOC | EV-SG-001/002/011 | [ ] Pass [ ] PWC [x] Fail [ ] TBD | 7 NCs open; no readiness closure package |
| DR-02 | Scope assignment / Scope-Zuordnung | P05 | VR-DOC | EV-SG-007/008 | [ ] Pass [ ] PWC [x] Fail [ ] TBD | Sampled project contract/wachbuch evidence not audit-proof |
| DR-03 | Critical evidence / Kritische Nachweise | P05 | VR-GATE / VR-DOC | EV-SG-004 to EV-SG-010 | [ ] Pass [ ] PWC [x] Fail [ ] TBD | Critical evidence not received |
| DR-04 | Technical review gate / Fachreview-Gate | P05 | VR-DOC / VR-EXP | EV-SG-011 | [ ] Pass [ ] PWC [ ] Fail [x] TBD | Templates and closure responses not yet reviewed |
| DR-05 | Start dataset and lead-time / Startdatensatz und Lead-Time | P05 | VR-PIL | EV-SG-011 | [ ] Pass [ ] PWC [ ] Fail [x] TBD | Lead-time measurement not complete |
| DR-06 | Requests, reviews, escalation / Nachforderungen, Reviews, Eskalation | P05 | VR-PROC / VR-CUST | EV-SG-011 | [ ] Pass [ ] PWC [ ] Fail [x] TBD | Request/review/escalation not measured |
| DR-07 | Client effort by service model / Kundenaufwand je Leistungsmodell | P05 | VR-PIL / VR-CUST | EV-SG-011 | [ ] Pass [ ] PWC [ ] Fail [x] TBD | Client effort estimated only |
| DR-08 | Task clarity / Aufgabenverständlichkeit | P05 | VR-GATE / VR-CUST | EV-SG-011 | [ ] Pass [ ] PWC [x] Fail [ ] TBD | Customer tasks not sent/confirmed |
| DR-09 | External partner/evidence path / Externe Partner-/Nachweislogik | P05 | VR-GATE / VR-PROC | EV-SG-006 | [ ] Pass [ ] PWC [x] Fail [ ] TBD | External partner dependency identified, path not closed |
| DR-10 | Audit-readiness network state / Audit-Readiness-Netzwerkzustand | P05 | VR-DOC | EV-SG-001/002 | [ ] Pass [ ] PWC [x] Fail [ ] TBD | Audit-readiness state red |
| DR-11 | SDL/object file minimum structure / Mindeststruktur SDL-/Objektakte | P05 | VR-DOC | EV-SG-007/008/009 | [ ] Pass [ ] PWC [x] Fail [ ] TBD | Object/personnel records incomplete |
| DR-12 | Audit package and final review / Auditpaket und finale Prüfung | P05 | VR-DOC / VR-AUD | EV-SG-003 | [ ] Pass [ ] PWC [x] Fail [ ] TBD | NC closure package not ready |
| DR-13 | Version and release control / Versions- und Freigabekontrolle | P05 | VR-DOC | EV-SG-008/011 | [ ] Pass [ ] PWC [x] Fail [ ] TBD | Evidence filing/retrieval failed for contract |
| DR-14 | Service model fit / Leistungsmodell-Fit | P05 | VR-CUST | EV-SG-011 | [ ] Pass [ ] PWC [ ] Fail [x] TBD | Service model fit to be evaluated |
| DR-15 | Software-only guardrail / Software-only-Schutzlogik |  | [VR-GATE/DOC/PIL/CUST/EXP/AUD/NEG] | EV- | [ ] Pass [ ] PWC [ ] Fail [ ] TBD |  |
| DR-16 | Value and growth path / Wert- und Wachstumspfad |  | [VR-GATE/DOC/PIL/CUST/EXP/AUD/NEG] | EV- | [ ] Pass [ ] PWC [ ] Fail [ ] TBD |  |
| DR-17 | Continuity/renewal / Betreuung/Renewal | P05 | VR-PROC | EV-SG-003/011 | [ ] Pass [ ] PWC [x] Fail [ ] TBD | Continuity process did not prevent Ü-audit findings |
| DR-18 | ZKM and measures / ZKM und Maßnahmen | P05 | VR-PROC | EV-SG-005/010 | [ ] Pass [ ] PWC [x] Fail [ ] TBD | Measures/IM protocol and environmental baseline not evidenced |
| DR-19 | Deadlines and recurrence / Fristen und Wiederholung | P05 | VR-PROC | EV-SG-003 | [ ] Pass [ ] PWC [ ] Fail [x] TBD | Deadline known; recurrence logic not tested |
| DR-20 | Status clarity / Statusklarheit | P05 | VR-CUST | EV-SG-011 | [ ] Pass [ ] PWC [x] Fail [ ] TBD | Status clarity for customer not yet provided |
| DR-21 | Responsibilities and next steps / Verantwortlichkeiten und nächste Schritte | P05 | VR-GATE | EV-SG-011 | [ ] Pass [ ] PWC [x] Fail [ ] TBD | Responsibilities/next steps not yet confirmed |
| DR-22 | Workforce readiness / Mitarbeiter- und Qualifikationsbereitschaft | P05 | VR-DOC | EV-SG-009 | [ ] Pass [ ] PWC [x] Fail [ ] TBD | Prokuristin personnel file missing |
| DR-23 | Expansion control / Erweiterungskontrolle |  | [VR-GATE/DOC/PIL/CUST/EXP/AUD/NEG] | EV- | [ ] Pass [ ] PWC [ ] Fail [ ] TBD |  |
| DR-24 | Knowledge and automation review / Wissens- und Automationsreview | P05 | VR-EXP | EV-SG-011 | [ ] Pass [ ] PWC [ ] Fail [x] TBD | Knowledge/tooling gaps identified; review pending |

# 11. Reverse Constraint Test Sheet RC-01 to RC-10 / Reverse-Constraint-Testblatt RC-01 bis RC-10

| RC-ID | Reverse constraint / Schutzanforderung | Test question / Testfrage | Project / Projekt | Evidence ID | Result / Ergebnis | Rework / Nacharbeit |
| --- | --- | --- | --- | --- | --- | --- |
| RC-01 | Avoid too much norm language / Zu viel Normsprache vermeiden | Are tasks action-oriented and understandable? / Sind Aufgaben handlungsorientiert und verständlich? | P05 | EV-SG-011 | [ ] Pass [ ] Fail [x] TBD | Risk: audit language must be translated into simple customer evidence tasks |
| RC-02 | Avoid platform/data capture overload / Überforderung durch Plattform/Datenerfassung vermeiden | Do forms, fields or status logic overwhelm small clients? / Überfordern Forms, Felder oder Statuslogik kleine Kunden? | P05 | EV-SG-011 | [ ] Pass [ ] Fail [x] TBD | Risk: grouped request may overload customer; track replies/confusion |
| RC-03 | Do not sell software-only to wrong segment / Software-only nicht an falsches Segment verkaufen | Was the selected model suitable? / War das gewählte Modell geeignet? |  | EV- | [ ] Pass [ ] Fail [ ] TBD |  |
| RC-04 | No unchecked automation / Keine ungeprüfte Automatisierung | Were audit-critical outputs reviewed? / Wurden auditkritische Outputs geprüft? | P05 | EV-SG-011 | [ ] Pass [ ] Fail [x] TBD | Templates/closure responses require expert review before submission |
| RC-05 | No unrealistic success guarantees / Keine unrealistischen Erfolgsgarantien | Was success promised without readiness evidence? / Wurde Erfolg ohne Readiness-Nachweis versprochen? |  | EV- | [ ] Pass [ ] Fail [ ] TBD |  |
| RC-06 | No generic project file only / Keine bloße generische Projektakte | Are SDL/object details really mapped? / Sind SDL-/Objektdetails wirklich abgebildet? |  | EV- | [ ] Pass [ ] Fail [ ] TBD |  |
| RC-07 | Dashboard/status must not feel like control pressure / Dashboard/Status darf nicht wie Kontrolldruck wirken | Does status logic help rather than pressure the client? / Hilft Statuslogik statt Druck zu erzeugen? | P05 | EV-SG-011 | [ ] Pass [ ] Fail [x] TBD | Email should be cooperative and relieving, not pressure-based |
| RC-08 | Partner network must not look like commission selling / Partnernetzwerk darf nicht wie Provisionsverkauf wirken | Is partner logic presented as evidence assurance? / Wird Partnerlogik als Nachweissicherung dargestellt? | P05 | EV-SG-006 | [ ] Pass [ ] Fail [x] TBD | Partner dependency must be framed as evidence assurance, not partner sale |
| RC-09 | No cheap-provider positioning / Keine Billiganbieter-Positionierung | Is the value/readiness argument clear? / Ist die Wert-/Readiness-Argumentation klar? |  | EV- | [ ] Pass [ ] Fail [ ] TBD |  |
| RC-10 | No broad expansion before stable security logic / Keine breite Expansion vor stabiler Sicherheitslogik | Are security-core processes stable before expansion? / Sind Sicherheitskernprozesse vor Erweiterung stabil? |  | EV- | [ ] Pass [ ] Fail [ ] TBD |  |

# 12. Auditor / Expert Review Record / Auditoren- oder Expertenreview

| Review item / Reviewobjekt | Question / Prüffrage | Finding / Befund | Result / Ergebnis | Evidence ID |
| --- | --- | --- | --- | --- |
| Audit package / Auditpaket | Complete, structured, audit-friendly? / Vollständig, strukturiert, auditfreundlich? | Not ready; closure package not prepared; DEKRA deviations captured | [ ] Pass [ ] PWC [x] Fail [ ] TBD | EV-SG-001/002/003 |
| Evidence matrix / Nachweismatrix | Are critical evidence items visible? / Sind kritische Nachweise sichtbar? | Initial evidence matrix exists, but closure proofs EV-SG-004 to EV-SG-010 are open | [ ] Pass [x] PWC [ ] Fail [ ] TBD | EV-SG-004 to EV-SG-011 |
| Scope matrix / Scope-Matrix | Is the certification scope clear? / Ist der Zertifizierungsumfang klar? | TBD; sampled project contract/wachbuch evidence pending | [ ] Pass [ ] PWC [ ] Fail [x] TBD | EV-SG-007/008 |
| SDL/object file / SDL-/Objektakte | Are object-related records easy to find? / Sind objektbezogene Nachweise auffindbar? |  | [ ] Pass [ ] PWC [ ] Fail [ ] TBD | EV- |
| Versions / Versionen | Are version and release status clear? / Sind Version und Freigabestatus klar? | Evidence filing/retrieval weakness: contract existed but was not found during audit | [ ] Pass [ ] PWC [x] Fail [ ] TBD | EV-SG-008 |
| Potential audit questions / Potenzielle Audit-Rückfragen | What would the auditor still ask? / Was würde der Auditor noch fragen? | Auditor will likely ask for signed instruction, IM protocol, annual report, Wachbuch check, contract, HR file, Strom/Wasser baseline | [ ] Pass [x] PWC [ ] Fail [ ] TBD | EV-SG-011 |

# 13. Data Quality Memo / Datenqualitätsmemo

| Question / Frage | Answer / Antwort | Comment / Kommentar |
| --- | --- | --- |
| Are all sources identified? / Sind alle Quellen identifiziert? | Yes - DFSS Measurement document, DEKRA deviation documentation, interview notes, HQ/OneDrive context | Closure evidence itself not yet received |
| Are owner, date and status available for each evidence item? / Sind Owner, Datum und Status je Evidenz vorhanden? | Partly - owner/date/status known for audit findings; closure evidence owners/dates mostly TBD | Customer M. Marquardt, Cert-Expert, Inductus dependency |
| Are any data contradictory? / Gibt es widersprüchliche Daten? | No direct contradictions; estimates are explicitly marked as estimates | Internal time <=2h and 5-6 customer actions are hypotheses, not measured values |
| Is the data sufficient for interpretation? / Reichen die Daten für Interpretation? | Sufficient for measurement activation and evidence request; not sufficient for Pilot Validation Report or final design | Need first customer request, returns, internal minutes, partner response, auditor acceptance |
| Which data must not be used? / Welche Daten dürfen nicht verwendet werden? | Unverified closure hypotheses; estimated hours/actions; assumed auditor acceptance; any missing customer/partner evidence | Do not use as accepted pilot evidence |
| Which data is still missing? / Welche Daten fehlen noch? | Customer evidence request send date; internal minutes; customer responses; Inductus/FASI/Betriebsarzt response; signed Mutterschutz instruction; IM protocol; Wachbuch excerpt; contract; HR file; Strom/Wasser baseline; auditor acceptance | Track from next action onward |

# 14. Calibration Memo / Kalibrierungsmemo

Do not set final target values. Only document evidence-based preliminary corridors if enough data exists. / Keine finalen Zielwerte setzen. Nur evidenzbasierte vorläufige Korridore dokumentieren, wenn genügend Daten vorliegen.

| Metric / Messgröße | Observed value / Beobachteter Wert | Data source / Datenquelle | Preliminary corridor? / Vorläufiger Korridor? | Confidence / Konfidenz | Decision / Entscheidung |
| --- | --- | --- | --- | --- | --- |
| Open NC count | 7 open NCs (5 major + 2 minor) | EV-SG-001/002 | [x] No [ ] Yes: ____ | [ ] Low [ ] Medium [x] High | [ ] Keep TBD [x] Use as preliminary calibration |
| Closure evidence received | 0/7 closure proofs received | Interview + EV-SG-004 to EV-SG-010 | [x] No [ ] Yes: ____ | [ ] Low [x] Medium [ ] High | [ ] Keep TBD [x] Use as preliminary calibration |
| Customer actions estimated | 5-6 actions estimated | Interview / EV-SG-011 | [x] No [ ] Yes: ____ | [x] Low [ ] Medium [ ] High | [x] Keep TBD [ ] Use as preliminary calibration |
| Internal closure effort estimate | <= 2h for M1/M2/M4/M5 only | Interview / EV-SG-011 | [x] No [ ] Yes: ____ | [x] Low [ ] Medium [ ] High | [x] Keep TBD [ ] Use as preliminary calibration |
| External partner dependency | Inductus/FASI/Betriebsarzt required; broader partner bottlenecks: FASI, Betriebsarzt, Elektriker, Versicherung, Fahrdienst | EV-SG-006 | [x] No [ ] Yes: ____ | [ ] Low [x] Medium [ ] High | [ ] Keep TBD [x] Use as preliminary calibration |
| Finding-to-request time | Start 2026-05-28; request date still TBD | EV-SG-001/011 | [x] No [ ] Yes: ____ | [ ] Low [x] Medium [ ] High | [x] Keep TBD [ ] Use as preliminary calibration |
|  |  | EV- | [ ] No [ ] Yes: ____ | [ ] Low [ ] Medium [ ] High | [ ] Keep TBD [ ] Use as preliminary calibration |
|  |  | EV- | [ ] No [ ] Yes: ____ | [ ] Low [ ] Medium [ ] High | [ ] Keep TBD [ ] Use as preliminary calibration |

# 15. Gate Decision Record / Gate-Entscheidungsprotokoll

| Gate question / Gate-Frage | Decision / Entscheidung | Evidence / Evidenz | Comment / Kommentar |
| --- | --- | --- | --- |
| Is the Pilot Validation Report allowed now? / Darf der Pilot Validation Report jetzt erstellt werden? | [x] No | EV-SG-001/002/003 | 0/7 NC closed; no closure proof received |
| Are S0 gates sufficiently evidenced? / Sind S0-Gates ausreichend belegt? | [x] No | S0 table / EV-SG-004 to EV-SG-011 | S0-03/S0-05/S0-06 fail; customer and partner evidence pending |
| Are reverse constraints tested? / Sind Reverse Constraints geprüft? | [x] No | RC table | Risks identified; tests not performed |
| Is data quality acceptable? / Ist Datenqualität akzeptabel? | [x] Partly | §13 | Data structure and NC facts sufficient; quantitative V-values and closure evidence not sufficient |
| Overall decision / Gesamtentscheidung | [x] DATA COLLECTION REQUIRED | Measurement active | Next: send evidence request, track minutes/responses, contact Inductus |

# 16. Status Values / Statuswerte

| Value / Wert | Meaning / Bedeutung |
| --- | --- |
| Pass | Requirement is fulfilled with acceptable evidence. / Anforderung ist mit akzeptierter Evidenz erfüllt. |
| Pass with Controls (PWC) | Usable with defined controls or rework actions. / Nutzbar mit definierten Controls oder Nacharbeit. |
| Fail | Requirement not fulfilled; blocker or rework required. / Anforderung nicht erfüllt; Blocker oder Nacharbeit erforderlich. |
| TBD | Not enough data yet; keep open. / Noch nicht genügend Daten; offen lassen. |
| Green / Grün | Basically audit-ready; only minor open items. / Grundsätzlich auditbereit; nur Kleinigkeiten offen. |
| Yellow / Gelb | Audit readiness possible, but important evidence/actions open. / Auditfähigkeit möglich, aber wichtige Nachweise/Aufgaben offen. |
| Red / Rot | Audit release not cleanly possible; S0 blocker exists. / Auditfreigabe nicht sauber möglich; S0-Blocker vorhanden. |

# 17. P05 NC Detail Map / Abweichungsdetailkarte

This section was added from the DEKRA deviation documentation and interview data. Closure actions are planned/evidenced only where explicitly marked; no NC is closed yet.

| NC | Class | Norm / clause | Auditor finding summary | Planned closure evidence | Current status |
| --- | --- | --- | --- | --- | --- |
| M1 | Major | ISO 45001 / 8.1.2 | No workplace-specific instruction of female employees regarding maternity protection; once-only instruction proof unavailable. | Create Mutterschutz-Unterweisung template; obtain signed workplace-specific instruction from affected female/prokuristin scope. | Open - no signed proof yet |
| M2 | Major | ISO 45001 / 5.4 | No evidence of consultation and participation of workers. | Use IM/IMS meeting protocol with date, topic, participants/confirmation and participation content. Add to process description. | Open - protocol evidence pending |
| M3 | Major | ISO 45001 / 6.1.4 | FASI/occupational physician services not sufficiently commissioned/site-specific; providers do not know company/new admin site; annual reports not prepared. | Contact Inductus; clarify service scope; obtain/commission site-specific service and annual report. | Open - external partner dependency |
| M4 | Major | ISO 45001 / 9.1 | No evidence of what Einsatzleiter checked; wachbuch only mentioned presence/partial check. | Wachbuch excerpt/template showing sample check by Einsatzleiter incl. Arbeitsschutz, Qualität, Umwelt, DIN/STL and customer requirements. | Open - customer Wachbuch evidence pending |
| M5 | Major | ISO 45001 / 8.1.1 | Contract for sampled current project could not be presented. | Contract exists but was not found; request again and file in audit-ready project evidence structure. | Open - evidence retrieval pending |
| m1 | Minor | ISO 45001 / 7.2 | No personnel documents for the Prokuristin available. | Request complete personnel file / basic HR documents, confidentiality, role/competence evidence as applicable. | Open - full file pending |
| m2 | Minor | ISO 14001 / 10.3 | After relocation, baseline values still being captured; no evidence for continual improvement of environmental performance. | Collect Strom/Wasser baseline after relocation via meter readings/invoices; Fuhrpark separate from relocation. | Open - baseline evidence pending |

# 18. Immediate Measurement Log Setup / Sofort-Messlogik

| Field | P05 value now | How to measure next |
| --- | --- | --- |
| Measurement start | 2026-05-28 (audit finding date) | Keep as official start; do not reset to later active work date |
| Next critical action | Grouped cooperative evidence request email | Record send date/time and requested evidence list |
| Internal work to create | Mutterschutz template; Wachbuch-Guide; Umweltkennzahlenblatt; IM/IMS protocol handling | Track minutes by document/action |
| Customer evidence required | HR file Prokuristin, signed Mutterschutz instruction, Wachbuch excerpt, sampled project contract, Strom/Wasser baseline | Track requested/received/submitted/accepted status |
| External evidence required | Inductus/FASI/Betriebsarzt annual report/service proof | Track contact date, response date, result and escalation |
| Do not use as evidence | Estimated <=2h, estimated 5-6 customer actions, assumed easy closure | Use as hypotheses only until measured |