DFSS Pilot Measurement Activation - Historical Delta Audit Case

P-HIST-02 | LC Security Extension / Event SDL Delta Audit | Filled with real project data

Cert-Expert | DMADV / Pilot Measurement Activation | 2026-06-05

Working boundary: No invented pilot data, no invented target values, no Product Design, no UI, no data model, no software architecture. This document captures a historical completed delta-audit / SDL-extension case and separates confirmed data, estimates, source-backed facts and open evidence fields.

Data status: Historical real project data from user interview plus screenshot of employee/SDL qualification matrix. This case is usable for development-readiness learning about extension audits, event SDLs, SK/EK/DA creation, Tool 2 MVP usage and follow-up evidence control.

# 0. Quick Status / Schnellstatus

| Question / Frage | Answer / Antwort |
| --- | --- |
| Are real historical pilot/baseline values available? | [x] Partly to strongly - real dates, scope, audit result, follow-up evidence list, tool usage and effort estimates are available. Full audit report and exact file evidence should be attached later if needed. |
| Can this case be used for DFSS design input? | [x] Yes - as delta-audit / SDL-extension / Tool-2-transition evidence. Not as normal initial-certification baseline. |
| Can a Pilot Validation Report be created from this alone? | [x] No - combine with P05 SecuGuard, P-HIST-01 LC Security initial certification, P-HIST-SC-01 TeamFlex and a live O2C/forms case. |
| Decision / Entscheidung | [x] Use as historical measurement input [ ] Rework [ ] Exclude |

# 1. Project Portfolio Overview / Projektportfolio-Uebersicht

| Project ID | Type | Norms / SDLs | Service model | Start / KSA | Audit | Main blocker / driver | Readiness |
| --- | --- | --- | --- | --- | --- | --- | --- |
| P-HIST-02 | Extension / delta audit / SDL-Erweiterung | DIN 77200-1: Veranstaltungsdienst; DIN 77200-2: Veranstaltungen mit besonderer Sicherheitsrelevanz | Done-for-you extension support; mixed manual e-mail + Tool 2 MVP usage | KSA 2026-02-23 | 2026-05-25; passed with follow-up evidence items | Security concept not available from event organizer; SK/EK/DA creation; event-specific evidence; employee/qualification readiness; Tool 2 bugs/organization | Audit passed; follow-up evidence controlled and later submitted according to user |

# 2. Project Setup Record / Projekt-Steckbrief

| Field / Feld | Input / Eingabe | Notes / Hinweise |
| --- | --- | --- |
| Project ID | P-HIST-02 | Historical completed delta-audit / SDL-extension case. |
| Customer | LC Security / LC Security & Service | Customer name used as historical working reference. |
| Project type | Extension audit / Delta-Audit / Zusatzbeauftragung | Not initial certification; extension of certified SDL scope. |
| KSA date | 2026-02-23 | KSA submitted to DEKRA according to user. |
| Audit date | 2026-05-25 | Extension/delta audit date according to user. |
| DIN 77200-1 SDL | Veranstaltungsdienst | Part 1 extension. |
| DIN 77200-2 SDL | Veranstaltungen mit besonderer Sicherheitsrelevanz | Part 2 extension; event-specific complexity. |
| Audit result | Passed | No formal NCs reported; follow-up evidence items were written down and later submitted. |
| Tool usage | Tool 2 definitely used | Tool 2 used for employee records / training / instruction packages; bugs and workflow friction observed. |
| Primary development relevance | Tool 2, SK-Bot, EK-Bot, event-specific ODA/DA logic, follow-up evidence management | Direct bridge from manual process into MVP/tool-supported workflow. |

# 3. Timeline Capture / Zeitpunkterfassung

| Timepoint | Value | Comment | Evidence ID |
| --- | --- | --- | --- |
| KSA submitted | 2026-02-23 | KSA submitted to DEKRA; audit later coordinated with auditor. | EV-LCEXT-001 |
| Audit coordination | Before 2026-05-25 | Audit agreed with auditor; special issue around unavailable organizer security concept was discussed with DEKRA expert/fachlicher Ausschuss contact. | EV-LCEXT-002 |
| Audit date | 2026-05-25 | Extension/delta audit for event SDLs. | EV-LCEXT-003 |
| Audit result | Passed | Passed with follow-up evidence items; not reported as major/minor NCs. | EV-LCEXT-004 |
| Follow-up evidence submission | After audit; exact date TBD | Follow-up evidence including contract/additional assignment and event documents later submitted according to user. | EV-LCEXT-005 |
| Post-audit follow-up effort | One afternoon / approx. 2-3 hours | User reports follow-up evidence work completed in roughly 2-3 hours. | EV-LCEXT-EST-001 |

# 4. Scope, SDL and Audit-Time Driver Addendum

| Driver / Treiber | Observed value / Beobachtung | DFSS relevance / DFSS-Relevanz |
| --- | --- | --- |
| SDL extension vs initial certification | Existing certification was extended by event-related SDLs | Extension audits need a separate workflow from initial certification and surveillance/NC closure. |
| DIN 77200-1 Veranstaltungsdienst | New Part 1 SDL added | Requires offer/contract, service documentation, event instruction and employee readiness. |
| DIN 77200-2 besondere Sicherheitsrelevanz | Event with special security relevance | Higher evidence complexity: SK, EK, DA, incident forms, event briefing and special qualification logic. |
| Missing organizer SK | Original security concept not accessible | Critical external evidence dependency; drove exceptional self-created security concept and DEKRA expert clarification. |
| Tool 2 MVP use | Tool 2 used for employee/training/instruction packages | Strong development evidence: useful chunk processing, but bugfix/server migration/organization improvements required. |
| Follow-up evidence | Multiple items written down and later submitted | Confirms need for structured follow-up evidence management, not loose e-mail memory. |

# 5. Evidence Requirement Map / Nachweisanforderungen

| Evidence group | Required / delivered evidence | Observed handling in LC Extension |
| --- | --- | --- |
| Certification data | Certificate numbers for DIN 77200 and ISO 9001 | Follow-up evidence item. |
| Employee / scope list | Current list of security employees / DEKRA XS table | Follow-up evidence item and basis for employee/SDL readiness. |
| Security concept | Security concept for event, final version | Major creation effort; exceptional because organizer SK was not available. |
| Deployment concept | Einsatzkonzept Veranstaltung, final version | Created / finalized as part of event evidence package. |
| Service/event instructions | Dienstanweisungen Veranstaltung, final versions | Created / finalized; event-specific DA logic differs from standard object-related service instruction. |
| Operational log evidence | 1 completed Wachbuch entry | Follow-up evidence item. |
| Incident reporting | Blank incident report form for event occurrences | Follow-up evidence item; supports event-specific reporting/escalation. |
| Offer documentation | Offer documentation, ideally event-related | Follow-up evidence item. |
| Contract / additional assignment | Additional assignment Karneval der Kulturen / second contract | Customer had to obtain/submit it later; critical contract evidence. |
| Uniform/equipment evidence | Current clothing issue proof for SMA Naje Razouk | Follow-up employee/equipment evidence item. |
| Qualification proof | Sachkunde proof for SMA Can Demirdag | Follow-up qualification evidence item. |
| Event briefing / instruction | Signed employee briefing / acknowledgement lists for event DA and on-site instructions | Follow-up workforce-readiness evidence item. |

# 6. Tool 2 / Workforce Readiness Learning

| Learning area | Observed fact | DFSS interpretation |
| --- | --- | --- |
| Tool 2 use | Tool 2 definitely used for employee/training/instruction package creation | Strong evidence for Tool 2 as necessary production engine component. |
| Bugs / organization | First bugs and organizational friction became visible | Development backlog input: bugfixes, workflow organization, server migration and connection logic. |
| Chunk processing | User developed a strategy to process larger chunks quickly and with fewer errors after preparation | Potential future process principle: batch processing of employee/SDL packages with QA checkpoints. |
| Employee/SDL matrix | Screenshot shows multiple employees with combinations of qualifications and SDL permissions | Confirms need for matrix logic: who may perform which SDL under which qualification/training status. |
| Quality assurance | Tool-supported package generation supported better QA than manual one-off creation | Supports Tool 2 stabilization before broader scaling. |

# 7. Screenshot Evidence - Employee / SDL Matrix

Figure 1: Screenshot supplied by user showing employee qualification and SDL allocation matrix for LC Security extension context. Names and Bewacher IDs were intentionally omitted by the user.

# 8. Effort / Aufwand Capture

| Work package | Effort / Aufwand | Notes |
| --- | --- | --- |
| Security concept learning and preparation | Approx. one week calendar time, not 8h/day | First intensive re-engagement with security concepts; included research, structuring, ChatGPT board/structure work and iterative V1 development. |
| Final production sprint | Approx. 3 intense days directly before audit, including late-night work | High stress; SK/EK/DA, employee packages and final evidence completion. |
| Follow-up evidence submission | Approx. 2-3 hours / one afternoon | Follow-up evidence after audit was completed relatively quickly. |
| Customer-side dependency | Additional assignment / contract evidence had to be obtained after audit | Contract was not available before audit; later submitted and resolved according to user. |
| Total effort classification | High effort / special event case | Do not use as normal effort target; use as development evidence for SK/EK/Tool2 bottlenecks. |

# 9. DFSS DR / S0 / RC Impact Mapping

| DR / Gate / RC | Impact from P-HIST-02 | Interpretation |
| --- | --- | --- |
| DR-02 Scope assignment | Two event SDLs with separate Part 1 / Part 2 logic | Scope must map SDL, event/project, evidence, employees and responsibility. |
| DR-03 Critical evidence | SK, EK, DA, contract, offer, employee list and qualifications required follow-up | Critical evidence cannot be loose; accepted follow-up logic must be visible. |
| DR-04 Fachreview / automation review | Self-created SK under exception required DEKRA/expert clarification | High-risk documents need expert review before release. |
| DR-11 SDL-/Objektakte | Event project evidence package is distinct from standard object file | Certification OS / project logic must support event-specific project files. |
| DR-22 Workforce readiness | Matrix of qualifications, trainings and SDL assignments required | Tool 2 and qualification engine are core to readiness. |
| S0-03 | Critical evidence incomplete at audit but accepted as follow-up | S0 gate should allow accepted Nachreichlogik, but must document it. |
| S0-04 | SK/EK/DA need review gate | No audit-critical output without fachliche Freigabe. |
| RC-04 | Risk of unchecked automation for SK/EK | Bots must not generate audit-critical event concepts without review. |
| RC-06 | Project file must not be generic | Event SDLs need specific evidence structure, not a generic certification folder. |

# 10. Development Readiness Learning

| Confirmed development need | Evidence from case | Priority implication |
| --- | --- | --- |
| SK-Bot / Security Concept Bot | Security concept was the largest special effort and key stress factor | High - but requires expert review and clear input limits. |
| EK-Bot / Deployment Concept Bot | Einsatzkonzept had to be created in connection with the event SK | High - paired with SK logic. |
| Event DA / ODA logic | Event-related service instruction had to be created/finalized | High for DIN 77200 event SDLs. |
| Tool 2 stabilization | Tool 2 was useful but bugs/organization created friction | Immediate development backlog before scaling. |
| Employee/SDL matrix | Multiple employee/qualification/SDL combinations visible | Core data logic for Tool 2 and Certification OS. |
| Follow-up evidence board | Multiple post-audit evidence items had to be tracked | Need for measures/evidence checklist, not e-mail memory. |

# 11. Data Quality Memo

| Data field | Quality | Comment |
| --- | --- | --- |
| Dates KSA / audit | Medium to high | User-provided exact dates; should be linked to KSA/e-mail/audit evidence later. |
| Audit result | Medium | User confirms passed; audit report not attached in this dataset. |
| Follow-up evidence list | High | Detailed user-provided list of follow-up items. |
| Effort estimates | Medium | Usable as historical effort estimate, not calibrated target. |
| Tool 2 usage | High | User corrected earlier uncertainty and confirmed Tool 2 was used definitely. |
| Screenshot matrix | Medium to high | Visual supporting evidence for workforce/SDL logic; names/IDs omitted intentionally. |

# 12. Gate Recommendation

Recommendation: Use P-HIST-02 as a historical delta-audit / SDL-extension / Tool-2-transition case in the cross-case baseline synthesis. The case is strong enough to support controlled transition toward development planning, especially for Tool 2 stabilization, SK/EK/DA bot requirements, event-SDL project file logic and follow-up evidence management. It should not be used as a statistical effort benchmark or as a proof that complex event SDLs can be standardized without expert review.